## Sheet1
Pages | Desining (Hours) | API(Hours)
Module - Members
Member login | 5 | 3
Privacy policy in app browser | 2 | 1
OTP Based verification for forgot password | 3 | 5
Home page with post and story | 20 | 14
Search and filter members profile | 8 | 4
Article with photos | 8 | 6
Polls with percentage | 8 | 10
Upload story and post and article | 8 | 4
Remember login | 2 | 1
Profile page with own all posts and article and reviews | 20 | 14
User login | 5 | 3
User registration | 3 | 3
Privacy policy in app browser | 1 | 1
OTP Based verification | 3 | 5
Home page with post and story | 30 | 10
Search and filter members profile | 8 | 2
Article with photos | 8 | 6
Polls with percentage | 8 | 10
Issues form submission with current ward members with photo | 8 | 16
Auto populate Ward no using society name | 8 | 6
Auto populate society list by pincode | 8 | 6
Rating system for members | 4 | 2
Remember login | 3 | 4
Module - Admin |  |  | Development
Login |  |  | 4
Member Data |  |  | 16
User Data |  |  | 12
Add member |  |  | 6
Issue form |  |  | 6
All data download option |  |  | 15
Summary dashboard |  |  | 16-24