## Sheet1
No | Additional changes |  | Hours | Priority | Pixidium notes | Work on | Completed | Negotiate
1 | Fixing bugs – slow load, touch screen wallet, zoom and scroll issues - Done | Done | 12 | High |  | ok |  | top many hrs max 4
2 | Landing Screens / Splash screen | InProgress | 14 |  |  |  |  | too many hrs max 4-6
3 | Video in circle, Swipe circle - Done | Done | 1 |  |  | ok
4 | Image Height and width issue - Done | Done | 1 |  |  | ok
5 | Swipe option in images - Done | Done | 4 |  |  | ok
6 | Read more, Read less-Done | Done | 1 |  |  | ok
7 | Dashboard visual data | Pending | 24 |  |  | ok
8 | Notifications ( Accept, reject and preview ) | Done | 8 | High |  | ok
9 | Share data |  | 2 |  | This function is already available and tested on my app on my ios |  | ok
10 | Wallet |  | 8 |  |  |  | ok
11 | Order screen and add to cart screen design and functional changes |  | 12 | High |  | ok
12 | Passcode UI issue and reset | Done | 4 | High |  |  | ok
13 | Bonus |  | 8 |  |  |  | ok
14 | Portfolio escrow ( deposite money into wallet ) |  | 5 |  |  |  | ok
15 | Stripe and Bank account Withdraw |  | 10 |  |  |  | ok
16 | Account settings Clear cache Community Guideline Terms & Service Privacy policy Copyright policy | Pending | 16 | Low |  | ok
17 | Use Dark Mode |  | 12 | Low |  | ok |  | later stage
18 | IOS create build, issue solving and upload into APP Store |  | 24 | High |  |  |  | too many hrs at once - lets look at them as and when required
| Total |  | 166